## Sheet1
System Name: CIT-U Students Organization Management System
Members:
Felraine Kyle A. Cataos
Kinka B. Sugimoto
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September |  |  |  | October
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. ERD MODEL
1.1. Creating Conceptual Data Model | Kinka B. Sugimoto | 2024-08-28 | 2024-08-28 | Done
1.2. Creating Logical Data Model | Felraine Kyle A. Cataos | 2024-08-28 | 2024-08-28 | Done
1.3. Creating Physical Data Model | Kinka B. Sugimoto | 2024-08-28 | 2024-08-28 | Done
1.4. Creation of Functional Business Requirements | Kinka B. Sugimoto & Felraine Kyle A. Cataos | 2024-09-02 | 2024-09-09 | Done
2. Making of UI/UX in Figma
2.1 Wireframing
2.1.1 Wireframe Dashboard Screen | Kinka B. Sugimoto | 2024-09-16 | 2024-10-02 | Done
2.1.2 Wireframe Login/Signup Screen | Kinka B. Sugimoto | 2024-09-16 | 2024-10-02 | Done
2.1.3 Wireframe Calendar Screen | Felraine Kyle A. Cataos | 2024-09-16 | 2024-10-02 | Done
2.1.3 Wireframe Members List Screen | Felraine Kyle A. Cataos | 2024-09-16 | 2024-10-02 | Done
2.2 Design UI/UX Screens
2.2.1 Design UI/UX Dashboard Screen | Kinka B. Sugimoto | 2024-09-23 | 2024-10-13 | Done
2.2.2 Design UI/UX Login/Signup Screen | Kinka B. Sugimoto | 2024-09-23 | 2024-10-13 | Done
2.2.3 Design UI/UX Calendar Screen | Felraine Kyle A. Cataos | 2024-09-23 | 2024-10-13 | Done
2.2.4 Design UI/UX Members List Screen | Felraine Kyle A. Cataos | 2024-09-23 | 2024-10-13 | Done