## Sheet1
System Name: CIT-U Students Organization Management System
Members:
Felraine Kyle A. Cataos
Kinka B. Sugimoto
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. Creation of ERD | Kinka Sugimoto & Felraine Cataos | 2024-04-09 | 2024-04-09 | Finished
1.2 Creation of Functional Business Requirements | Kinka Sugimoto & Felraine Cataos | 2024-09-09 | 2024-09-09 | Finished
2. Start creating UI/UX using Figma | Kinka Sugimoto & Felraine Cataos |  |  | To-do